## Sheet 1 - Snags for 22 Arnold C
Snags for 22 Arnold Close
PLOT 136
| Snags | Status | Reported | Comment | Allocation
1 | Utility door threshold split | Open | Y | Hometech visited and mentioned that filling in the split, would not make much difference. Agreement with Site to get this fixed properly | Site
2 | Meter lock and door broken | Open | Y | Not done | Site
3 | Front door window lead damaged | Open | Y | Not done | Customer Service
4 | Dead Grass | Open | Y | Not done. Front garden edges and dead patches in back garden | Landscapers
5 | Alarm sensitivity | Open | Y | Advised by alarm company (Matthew Crump) that a new alarm panel will be ordered and fitted to see if it makes any difference. Awaiting feedback. | Customer Service
6 | Bathroom threshold strip damaged | Fixed | Y | Fixed by Amco (14th July 2017), but bathroom door no longer closes properly. See 14. | Customer Service
7 | Mastic needed in bathroom around skirting, toilet and bath panel | Fixed | Y | Done. | Completed
8 | Small hole in floor grout in bathroom near door threshold | Closed | Y | New bathroom threshold strip covers this - See 6, so can be closed | Customer Service
9 | General touch up | Fixed | Y | To include: Painting of lounge door - sanded down by Redrow tradesman (Dan) as it had multiple paint drip marks on it - 5th July 2017. Items: 11, 12, 13, 15 (excluding 26) Dents at top of stairs on bannister and skirting, still remaining from Site Chips in door frame in bedrooms 3 Small hole in wall in snug Chip in skirting near front door Paint touch up on skirting board in wardrobe in bedroom 1 Chips and marks on kitchen door frame Paint touch up in cloaks Paint touch up on landing window sill Paint touch up on bathroom skirting following tiling works. Paint touch up on conservatory skirting and under sills | Customer Service except numbers 22 23 25 and 27 which will be completed by site
10 | Replacement kitchen cupboard door (under sink) | Open | Y | The second replacement door to come from Symphony (12th July 2017) has a defect at the bottom of the door. This was recorded on the worksheet when the work was signed for. Symphony (Dave) mentioned that a new one would be ordered and they would come back out to fit it. | Customer Service
11 | Stiff lock on ensuite 2 door | Fixed | Y | Customer Services (Jane) mentioned that she would ask for this to be attended to when the general touch up is done. We managed to fix this following ScrewFix damaging the lock trying to repair it. | Customer Service
12 | Small chip in tile in hallway | Open | Y | Not done | Site
13 | Major shrinkage cracks under conservatory sills | Temporary Fix | Y | ScrewFix applied a temporary fix, so there may be further shrinkage cracks appearing when other cracks around the house are addressed (See 26). | Customer Service
14 | Bathroom door scrapes new threshold strip | Fixed | Y | ScrewFix sorted this out. See 6. | Customer Service
15 | Cracks behind towel radiator in bathroom | Fixed | Y | When the towel radiator was replaced and fitted, damage was caused on the wall behind it. Cracks have appeared around the towel radiator pipes. | Customer Service
16 | Ensuite 1 and ensuite 2 discolouration | Open | Y | Followed up by email to Site (Ben Rolph) on the 29th June, 3rd July and on the 9th July 2017 as this work was not completed properly as the tilers ran out of stain. Ben was shown the incomplete finish and agreed that the work was “patchy” in the ensuites. He mentioned he would arrange for the tilers to come back out. | Site
17 | Fencing coming away in back garden where it meets the neighbours garage | Open | Y | Not done | Site
18 | Front garden to be dressed | Open | Y | We reported the sunken edges of the front lawn to Site and were advised to water the grass daily to encourage new grass to grow round the edges and then Site would arrange to dress it. We have been watering the lawn daily since. | Site
19 | Door stops for fitted wardrobes in bedroom 1 | Open | Y | Customer Services (Jane) and Site (Ben) mentioned that Hammonds would supply these (and we were told that Hammonds had put some aside for us). We were expecting delivery of these w/c 15th July 17. | Hammonds
20 | Bathroom door stop to be fitted | Open | Y | Following tiling works the bathroom door stop has not been put back in place. | Site
21 | Loose slabs / badly cut slabs | Open | Y | When Site came round to do this work, they did not do all the loose slabs which we reported back on the same day. The cracked slab at the back is fixed. The cracked slab that was replaced at the front of the house by Site, is raised and is a trip hazard. The cracked slab at the back / side by the manhole cover, was cut badly and needs to be replaced. Ben mentioned that he would arrange for Site to come back out and rectify the slab work, as they cut the slabs on site to avoid doing this in the garden and the measurements were not quite right. | Customer Service
22 | The frame of the interior door (from kitchen) in the utility is chipped | Open | Y | Not done | Site
23 | Silicone seal above worktops (kitchen and utility) | Open | Y | Not done (although Symphony kindly did one edge for us but ran out of time). | Site
24 | Untidy finish on conservatory window sills | Open | Y | Not done | Site
25 | Mastic in ensuites on top of tiles (in corners) needs rectifying | Open | Y | Not done | Site
26 | General cracks around door frames and windows – shrinkage | Open | Y | Partially done. Not all the cracks on the windows and doors have been rectified. | Customer Service
27 | Mastic to hall, cloaks, kitchen, utility, conservatory | Open | Y | Partially done, but not complete. Work remaining in all areas. Some of this requires wood filler for the skirting. | Site
28 | Water stain in conservatory | Open | Y | Stain block has been applied to the wall and Site mentioned to monitor this in case it was the conservatory roof that was leaking. This has therefore been left open. | Site